## Instructions
Digital Media Planning Workflow Calculator
There are two approaches you can take with this calculator:
1) Activity-based costing method
2) Top-down method
To use one of these approaches, click on the appropriate worksheet tab below.
We recommend using both approaches because one will validate the other.
Legal CYA - this calculator is provided "as is" and no warranty is given that the calculations
are correct.
That said, we did our best and we hope you find it useful!
If you have any questions or want to try our digital media planning tools,
visit us at www.NextMark.com
or call us at (603) 643-1307
© 2011 NextMark, Inc.

## Activity-based Costing Method
How Much Does it Cost to Create and Execute a Digital Media Plan?
Scenario: $500k budget, 10 sites @ $50k each with 10 placements avg.
|  |  |  | Number of Hours by Function per campaign | [21 empty] | 290.9091 | 218.1818 | 109.0909 | 72.7273 | 72.7273 | 50.9091 | 160 | 101.8182 | 58.1818 | 47.2727 | 40
Phase | Task | TOTAL PROJECT HOURS |  | VP, Digital |  | Media Director |  | Supervisor |  | Media Planner |  | Assistant Planner |  | Media Buyer |  | Director of Ad Operations |  | Campaign Supervisor |  | Campaign Manager |  | Ad Trafficker |  | Campaign Coordinator |  | VP, Digital | Media Director | Supervisor | Media Planner | Assistant Planner | Media Buyer | Director of Ad Operations | Campaign Supervisor | Campaign Manager | Ad Trafficker | Campaign Coordinator | Cost
Project Scope | Scope of Work Definition | 10 | 2.073% | 3 | 30% | 3 | 30% | 2 | 20% | 1 | 10% | 0 | 0% | 0 | 0% | 1 | 10% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 872.7273 | 654.5455 | 218.1818 | 72.7273 |  |  | 160 |  |  |  |  | 1978.1818
| TOTAL PROJECT SCOPE | 10 | 2.073% | 3 | 30% | 3 | 30% | 2 | 20% | 1 | 1.887% | 0 | 0% | 0 | 0% | 1 | 4.878% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 872.7273 | 654.5455 | 218.1818 | 72.7273 |  |  | 160 |  |  |  |  | 1978.1818
Strategy | Brainstorming Session | 21 | 4.352% | 5 | 23.81% | 5 | 23.81% | 5 | 23.81% | 0 | 0% | 0 | 0% | 0 | 0% | 6 | 28.57% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 1454.5455 | 1090.9091 | 545.4545 |  |  |  | 960 |  |  |  |  | 4050.9091
| Audit History / research / data review | 14 | 2.902% | 1 | 7.143% | 2 | 14.29% | 1 | 7.143% | 1 | 7.143% | 0 | 0% | 0 | 0% | 3 | 21.43% | 1 | 7.143% | 5 | 35.71% | 0 | 0% | 0 | 0% | 290.9091 | 436.3636 | 109.0909 | 72.7273 |  |  | 480 | 101.8182 | 290.9091 |  |  | 1781.8182
| Media Brief | 5.5 | 1.14% | 0 | 0% | 1 | 18.18% | 4 | 72.73% | 0 | 0% | 0 | 0% | 0 | 0% | 0.5 | 9.091% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 218.1818 | 436.3636 |  |  |  | 80 |  |  |  |  | 734.5455
| Target Audience Definition | 6 | 1.244% | 1 | 16.67% | 2 | 33.33% | 3 | 50% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 290.9091 | 436.3636 | 327.2727 | [8 empty] | 1054.5455
| Develop / Agree on Objectives | 6 | 1.244% | 1 | 16.67% | 1 | 16.67% | 3 | 50% | 0 | 0% | 0 | 0% | 0 | 0% | 1 | 16.67% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 290.9091 | 218.1818 | 327.2727 |  |  |  | 160 |  |  |  |  | 996.3636
| Prepare Strategic Plan | 16 | 3.316% | 3 | 18.75% | 5 | 31.25% | 8 | 50% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 872.7273 | 1090.9091 | 872.7273 | [8 empty] | 2836.3636
| TOTAL STRATEGY | 68.5 | 14.2% | 11 | 16.06% | 16 | 23.36% | 24 | 35.04% | 1 | 1.887% | 0 | 0% | 0 | 0% | 10.5 | 51.22% | 1 | 2.381% | 5 | 5.556% | 0 | 0% | 0 | 0% | [11 empty] | 11454.5455
Planning | Develop Consideration Set | 17 | 3.523% | 0 | 0% | 1 | 5.882% | 1 | 5.882% | 10 | 58.82% | 5 | 29.41% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 218.1818 | 109.0909 | 727.2727 | 363.6364 | [6 empty] | 1418.1818
| Send RFPs | 3 | 0.6218% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 3 | 100% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  |  |  |  | 218.1818 | [6 empty] | 218.1818
| Collect Proposals | 1 | 0.2073% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 1 | 100% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  |  |  |  | 72.7273 | [6 empty] | 72.7273
| Evaluate Proposals | 17 | 3.523% | 0 | 0% | 0 | 0% | 2 | 11.76% | 10 | 58.82% | 5 | 29.41% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  |  | 218.1818 | 727.2727 | 363.6364 | [6 empty] | 1309.0909
| Negotiate / Prepare Buy options | 20 | 4.145% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 20 | 100% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | [5 empty] | 1018.1818 | [5 empty] | 1018.1818
| Finalize Media Plan | 15 | 3.109% | 0 | 0% | 0 | 0% | 0 | 0% | 10 | 66.67% | 0 | 0% | 5 | 33.33% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  |  |  | 727.2727 |  | 254.5455 | [5 empty] | 981.8182
| Prepare and Deliver Client Presentation | 14 | 2.902% | 1 | 7.143% | 1 | 7.143% | 4 | 28.57% | 5 | 35.71% | 3 | 21.43% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 290.9091 | 218.1818 | 436.3636 | 363.6364 | 218.1818 | [6 empty] | 1527.2727
| Revise Media Plan | 5 | 1.036% | 0 | 0% | 0 | 0% | 0 | 0% | 5 | 100% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  |  |  | 363.6364 | [7 empty] | 363.6364
| Get Media Authorization | 1 | 0.2073% | 0 | 0% | 0 | 0% | 1 | 100% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  |  | 109.0909 | [8 empty] | 109.0909
| TOTAL PLANNING | 93 | 19.27% | 1 | 1.075% | 2 | 2.151% | 8 | 8.602% | 40 | 43.01% | 17 | 18.28% | 25 | 26.88% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | [11 empty] | 7018.1818
Implementation | Issue Insertion Orders to Publishers | 2 | 0.4145% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 2 | 100% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  |  |  |  | 145.4545 | [6 empty] | 145.4545
| Collect Insertion Orders from Publishers | 3 | 0.6218% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 3 | 100% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  |  |  |  | 218.1818 | [6 empty] | 218.1818
| Get Creative Specs | 5 | 1.036% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 5 | 100% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  |  |  |  | 363.6364 | [6 empty] | 363.6364
| Gather creative Assets | 47 | 9.741% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 2 | 4.255% | 5 | 10.64% | 30 | 63.83% | 0 | 0% | 10 | 21.28% | [6 empty] | 320 | 509.0909 | 1745.4545 |  | 400 | 2974.5455
| Build Tags | 20 | 4.145% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 20 | 100% | 0 | 0% | [9 empty] | 945.4545 |  | 945.4545
| Traffic Tags | 10 | 2.073% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 10 | 100% | 0 | 0% | [9 empty] | 472.7273 |  | 472.7273
| QA/Confirm Tags are up | 15 | 3.109% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 10 | 66.67% | 5 | 33.33% | [9 empty] | 472.7273 | 200 | 672.7273
| Bill Client | 12 | 2.487% | 0 | 0% | 0 | 0% | 0 | 0% | 5 | 41.67% | 5 | 41.67% | 0 | 0% | 2 | 16.67% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  |  |  | 363.6364 | 363.6364 |  | 320 |  |  |  |  | 1047.2727
| TOTAL IMPLEMENTATION | 114 | 23.63% | 0 | 0% | 0 | 0% | 0 | 0% | 5 | 4.386% | 15 | 13.16% | 0 | 0% | 4 | 3.509% | 5 | 4.386% | 30 | 26.32% | 40 | 35.09% | 15 | 13.16% | [11 empty] | 6840
Execution | Delivery Monitoring | 24 | 4.974% | 0 | 0% | 0 | 0% | 0 | 0% | 2 | 8.333% | 5 | 20.83% | 0 | 0% | 0 | 0% | 2 | 8.333% | 5 | 20.83% | 10 | 41.67% | 0 | 0% |  |  |  | 145.4545 | 363.6364 |  |  | 203.6364 | 290.9091 | 472.7273 |  | 1476.3636
| Optimization | 24 | 4.974% | 0 | 0% | 0 | 0% | 0 | 0% | 2 | 8.333% | 5 | 20.83% | 0 | 0% | 0 | 0% | 2 | 8.333% | 10 | 41.67% | 5 | 20.83% | 0 | 0% |  |  |  | 145.4545 | 363.6364 |  |  | 203.6364 | 581.8182 | 236.3636 |  | 1530.9091
| Monthly Invoices | 36 | 7.461% | 0 | 0% | 0 | 0% | 0 | 0% | 2 | 5.556% | 5 | 13.89% | 0 | 0% | 2 | 5.556% | 2 | 5.556% | 5 | 13.89% | 0 | 0% | 20 | 55.56% |  |  |  | 145.4545 | 363.6364 |  | 320 | 203.6364 | 290.9091 |  | 800 | 2123.6364
| TOTAL EXECUTION | 84 | 17.41% | 0 | 0% | 0 | 0% | 0 | 0% | 6 | 7.143% | 15 | 17.86% | 0 | 0% | 2 | 2.381% | 6 | 7.143% | 20 | 23.81% | 15 | 17.86% | 20 | 23.81% | [11 empty] | 5130.9091
Reporting | Campaign Reporting | 40 | 8.29% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 10 | 25% | 10 | 25% | 0 | 0% | 20 | 50% | [7 empty] | 1018.1818 | 581.8182 |  | 800 | 2400
| Reconcile Invoices | 40 | 8.29% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 10 | 25% | 10 | 25% | 0 | 0% | 20 | 50% | [7 empty] | 1018.1818 | 581.8182 |  | 800 | 2400
| Prepare and Deliver Client Presentation | 33 | 6.839% | 0 | 0% | 2 | 6.061% | 3 | 9.091% | 0 | 0% | 0 | 0% | 0 | 0% | 3 | 9.091% | 10 | 30.3% | 15 | 45.45% | 0 | 0% | 0 | 0% |  | 436.3636 | 327.2727 |  |  |  | 480 | 1018.1818 | 872.7273 |  |  | 3134.5455
| TOTAL REPORTING | 113 | 23.42% | 0 | 0% | 2 | 1.77% | 3 | 2.655% | 0 | 0% | 0 | 0% | 0 | 0% | 3 | 2.655% | 30 | 26.55% | 35 | 30.97% | 0 | 0% | 40 | 35.4% | [11 empty] | 7934.5455
Cost Per Media Plan |  | 482.5 | 100% | 15 | 3.109% | 23 | 4.767% | 37 | 7.668% | 53 | 10.98% | 47 | 9.741% | 25 | 5.181% | 20.5 | 4.249% | 42 | 8.705% | 90 | 18.65% | 55 | 11.4% | 75 | 15.54% | [11 empty] | 40356.3636
Cost Per Media Plan using "Top Down" Approach | [36 empty] | 40296
Difference (should be close to 0) | [36 empty] | 60.3636
Caveats That Impact Cost Per Media Plan Analysis
Compensation structure of the agency (i.e. project fee, hourly rate, commission, etc.)
Agency structure and assignment of roles and responsibilities to each position
Salaries for each position
Experience level of each person within each position
The efficiency of agency operations process and work flow
Changes in obectives, strategy, and campaign parameters
Account management demands dependent on client
Amount of research that needs to be conducted
Number of teams/agency partners involved (i.e. media, creative, promotions, CRM, etc.)
Size and number campaigns and the number of sites / placements considered
Complexity of deal structure (i.e. banners vs. custom integration)
The number of creative executions and formats
Implementation errors caused by media vendors
Tracking requirements, reporting needs, analytics, etc.
© 2011 NextMark, Inc.
Note on U27: Michelle Burnham: Inludes troubleshooting and project management with creative team & rich media vendor
Note on W28: Michelle Burnham: Based on 10 Sites w/ 10 placements each (100 Placements) with 2 creative executions
Note on W29: Michelle Burnham: Based on 10 Sites w/ 10 placements each (100 Placements)
Note on W30: Michelle Burnham: Based on 10 Sites w/ 10 placements each (100 Placements)
Note on Y30: Michelle Burnham: Based on 10 Sites w/ 10 placements each (100 Placements)
Note on B31: Michelle Burnham: This is the PreBill
Note on W34: Michelle Burnham: Executed the optimization plan
Note on B35: Michelle Burnham: Monthly Reconciliation Report
Note on U35: Michelle Burnham: Responsible for reviewing the Reconciliation Report
Note on Y35: Michelle Burnham: Based on 10 Sites w/ 10 Placements (100 Placements).
Note on Y38: Michelle Burnham: Based on 10 Sites w/ 10 Placements (100 Placements).

## Top Down Method
How Much Does it Cost to Create and Execute a Media Plan?
Staffing
Job Function | Annual Salary | Overhead Markup* | Profit Markup | Annual | Billable Hours | Hourly | Head Count | Allocation** | Contribution
VP, Digital | 200000 | 100% | 20% | 480000 | 1650 | 290.9091 | 1 | 50% | 240000
Media Director | 150000 | 100% | 20% | 360000 | 1650 | 218.1818 | 1 | 75% | 270000
Media Supervisor | 75000 | 100% | 20% | 180000 | 1650 | 109.0909 | 3 | 100% | 540000
Media Planner | 50000 | 100% | 20% | 120000 | 1650 | 72.7273 | 10 | 100% | 1200000
Media Buyer | 50000 | 100% | 20% | 120000 | 1650 | 72.7273 | 10 | 100% | 1200000
Assistant Media Planner | 35000 | 100% | 20% | 84000 | 1650 | 50.9091 | 20 | 100% | 1680000
Director of Ad Operations | 110000 | 100% | 20% | 264000 | 1650 | 160 | 1 | 100% | 264000
Campaign Supervisor | 70000 | 100% | 20% | 168000 | 1650 | 101.8182 | 5 | 100% | 840000
Campaign Manager | 40000 | 100% | 20% | 96000 | 1650 | 58.1818 | 10 | 100% | 960000
Ad Trafficker | 32500 | 100% | 20% | 78000 | 1650 | 47.2727 | 20 | 100% | 1560000
Campaign Coordinator | 27500 | 100% | 20% | 66000 | 1650 | 40 | 20 | 100% | 1320000
Totals | 840000 |  |  | 2016000 | 18150 | 111.0744 | 101 |  | 10074000
* "Overhead Markup" is the percentage of annual salary to cover people related expenses like payroll taxes, benefits, office space, phone, computer, etc.
** "Allocation" is the percentage of time dedicated to the creation and execution of media plans (versus other activities like sales)
Organizational Production
# of Media Plans / year |  | 250
Average Number of Media Programs per Media Plan |  | 10
Average Number of Placements per Site/Media Program |  | 10
Average Number of Placements per Media Plan |  | 100
# of Placements Per Year |  | 25000
Metrics
Cost Per Media Plan |  | 40296
Cost Per Placement |  | 402.96
© 2011 NextMark, Inc.